## Integration Plan
BUG_ID |  | Feature | TAG | S^N | Main Contributor | Package | IW0935 | IW0937 | IW0939 | IW0941 | IW0943 | IW0945 | IW0947 | IW0949 | IW0951 | IW1001 | 2010-Q1 | 2010-Q2 | 2010-Q3 | 2010-Q4
246-8 |  | Additional Kernel components backport for S^3 to S^2 | N/A | S^2 | DOCOMO/SOSCO | Kernel & Hardware Services | IW0939: 0
| -1 | New Comms Framework | 3PC | S^3 | NOKIA | Tech Domain Wide Features | IW0939: 0
| -1 | 3PC architecture | 3PC | S^3 | NOKIA | Comms Framework | IW0939: 0
|  | SymbianJ | Java | S^3 | NOKIA | SymbianJ | [10 empty] | 2
|  | S^3 SDK & ADT | Kits | S^3 | Symbian.org | N/A | [10 empty] | 3
|  | NFC OS Layer package contribution | NFC | S^3 | NOKIA | NFC | [10 empty] | 1
|  | NFC Services contribution | NFC | S^3 | NOKIA | NFC | [10 empty] | 1
|  | TBC | NFC | S^3 | NOKIA | Application packages
219 |  | Zoom2 Baseport | ExecEnv | S^3 | TI | BSP | IW0943: 2
179 |  | NGA adaptation | NGA | S^3 | NOKIA | Telephony Apps | IW0951: 3
182 |  | Basic Non-NGA Graphic Support | NGA | S^3 | NOKIA | Graphics | IW0939: FCL
235 | -1 | PC development platform | NGA | S^3 | NOKIA | Graphics | [10 empty] | 2
181 | -1 | Graphics surfaces and HW acceleration of graphics | NGA | S^3 | NOKIA | Graphics | IW0943: FCL; IW0945: 1
237 |  | Widget specific effects | NGA | S^3 | NOKIA | HomeScreen | IW0945: 3
238 |  | Homescreen background animation | NGA | S^3 | NOKIA | HomeScreen | IW0945: 3
245 |  | Symbian NGA support for video playback Link to feature description | NGA | S^3 | NOKIA | Video player | IW0941: 3
|  | TBC | SHAI | S^3 | NOKIA | TBC
|  | SMP prototype Kernel | SMP | S^3 | NOKIA | Kernel & Hardware Services | IW0939: 0
|  | Writeable demand paging | WDP | S^3 | NOKIA | Kernel & Hardware Services | IW0939: 0
434 |  | Contacts application UI revolution using QT | NewUI | S^4 | NOKIA | Contacts | [11 empty] | 3
|  | Qt-based Start up animation and splash screen | NewUI | S^4 | NOKIA | Generic_Applications_Support | [11 empty] | 3
|  | Qt Eclipse integration plugins version 1.5.2 | NewUI | S^3 | NOKIA | IDE
|  | Conversation based messaging direct touch UI using Qt | NewUI | S^4 | NOKIA | Messaging | [11 empty] | 3
|  | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | NewUI | S^4 | NOKIA | Phone | [13 empty] | 3
|  | Direct UI | NewUI | S^4 | NOKIA | Phone | [11 empty] | 3
|  | touch UI support (implementation of common UI API) | NewUI | S^4 | NOKIA | VideoTelephony | [11 empty] | 3
zzz
[5 empty] | Package owner MCL bulk contribution |  | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Individual Package Contributions
|  | IW = integration Window |  | 0 | Done |  | IW0941: 0; IW0943: Planned contribution not recieved or not useable
|  | IW is a 2 week cycle at the end produces a PDK |  | 1 | Issue: Late or not committed |  | IW0941: 1; IW0943: Planned contribution in this time frame
|  |  |  | 2 | At risk |  | IW0941: 2; IW0943: Planned contribution recieved
|  | BUG_ID - Good engagement with contributor. Timeframe provided |  | 3 | Planned and on track | bar: IW0935 to IW0937
|  | BUG_ID - Engagement with contributor is pending |  | FCL | FCL Drop planned/Available (if date in the past) |  | IW0943: -1; IW0945: "Heavy Duty" integration work
BUG_ID - too far into the future to start engaging beyond backlog data

## Integration Graph
|  | 1 | 17 | 6
Column Labels
| Values | S^2 | S^3 | S^4 | Grand Total | Values | S^2 | S^3 | S^4
| Count of IW0935 |  |  |  |  | Count of IW0935 | 1 | 17
| Count of IW0937 |  |  |  |  | Count of IW0937 | 1 | 17
| Count of IW0939 | 1 | 5 |  | 6 | Count of IW0939 | 0 | 12
| Count of IW0941 |  | 1 |  | 1 | Count of IW0941 |  | 11
| Count of IW0943 |  | 2 |  | 2 | Count of IW0943 |  | 9
| Count of IW0945 |  | 3 |  | 3 | Count of IW0945 |  | 6
| Count of IW0947 |  |  |  |  | Count of IW0947 |  | 6
| Count of IW0949 |  |  |  |  | Count of IW0949 |  | 6
| Count of IW0951 |  | 1 |  | 1 | Count of IW0951 |  | 5
| Count of IW1001 |  |  |  |  | Count of IW1001 |  | 5 | 6
| Count of 2010-Q1 |  | 5 |  | 5 | Count of 2010-Q1 |  | 0 | 6
| Count of 2010-Q2 |  |  | 5 | 5 | Count of 2010-Q2 |  | 0 | 1
| Count of 2010-Q3 |  |  |  |  | Count of 2010-Q3 |  | 0 | 1
| Count of 2010-Q4 |  |  | 1 | 1 | Count of 2010-Q4 |  | 0 | 0
| total | SMP SAFE Validated
os | 23 | 7
mw | 46 | 1

## SMP List
| Done |  |  | S^3 Targets
| Still in progress |  |  | S^4 Targets
| Delayed / PkO unaware |  |  | S^5 Targets
| Package | Tech Domain | OS layer | SMP Safe in Release | SMP safe Status | Comments
1 | boardsupport | OS Base services | OS | S^3 | Still work in progress | Emulator BSP - S^3 validated, HAI - stll work in progress. Timeframes to be made available shortly.
2 | bt | device connectivity | OS | S^3 | Still work in progress | Validated except for Atext component, completion time frames to be available shortly.
3 | buildtools | Tools | OS | S^3 | Done | PkO already confirmed this.
4 | cellularsrv | Personal comms | OS | S^3 | Still work in progress | Except for CTSY, PkO aims to complete this by Q4
5 | commsfw | Data communication | OS | S^3 | Done | PkO already confirmed this.
6 | deviceplatformrelease | Device Management | OS |  |  | Unowned package, update from Lars. Daniel Rubio to update on deprecation
7 | deviceserv | OS Base services | OS | S^3 | Still work in progress | SW components validated for S^3, HW components pending. Timeframe to be made available shortly.
8 | graphics | UI | OS | S^3 | 1H/09 , In progress | No response yet from PkO, recontacted again.
9 | imagingext | Multimedia | OS | S^3 | Still work in progress | PkO aims to complete this by wk 48
10 | kernelhwsrv | OS Base services | OS | S^3 | Done | PkO already confirmed this.
11 | lbs | Location | OS | S^3 | Done | PkO already confirmed this.
12 | mm | Multimedia | OS | S^3 | Done | PkO already confirmed this.
13 | networkingsrv | Data communication | OS | S^3 | 90% test cases done | PkO has responded to ensure 100% within S^3
14 | osrndtools | Tools | OS | S^3 | Still work in progress | PkO aims to complete this by Q4/2009
15 | ossrv | openservices???? | OS |  |  | deprecated? - check with lars | written kirill anyway...
16 | persistentdata | OS Base services | OS | S^3 | Done | PkO already confirmed this.
17 | security | security | OS | S^3 | Done | Pko already confirmed this.
18 | shortlinksrv | device connectivity | OS |  |  | No response yet from PkO, recontacted again.
19 | text andloc | UI | OS | S^3 | Still work in progress | PkO aims to complete this by wk48
20 | unref |  | OS |  |  | deprecated? - check with lars
21 | usb | device connectivity | OS | S^3 | Still work in progress | Pko aims to complete this by wk46
22 | wlan | Data communication | OS | S^3 | Still work in progress | PkO expects this to get over by week 48
23 | xmlsrv | Runtimes | OS | S^3 | Still work in progress | xmlsecurityengine is pending . PkO has assured validation before Q4/2009
24 | accesssec | Data communications | MW | S^4 | 2010 Q1 | PkO confirms this to be a S^4 target
25 | appinstall | Runtimes | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
26 | appsupport |  | MW | S^3 | Still work in progress | PkO expects this to get over by week 50
27 | btservices | Device connectivity | MW |  | Done | PkO has confirmed this
28 | camerasrv | Multimedia applications | MW |  |  | PkO is unaware until now.
29 | classicui | UI | MW |  |  | PkO is unaware until now.
30 | dlnasrv | Device connectivity | MW | S^4 |  | PkO confirms this to be a S^4 target
31 | drm | Security | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
32 | gsprofile |  |  |  |  | check with Lars
33 | hapticsservices | UI | MW |  |  | PkO is unaware until now.
34 | helix | ?????? | MW | S^3 | Still work in progress | PkO expects this to get over by week 50
35 | homescreensrv | UI | MW |  |  | PkO is unaware until now.
36 | imghandling | Multimedia | MW |  |  | Pko us unaware until now
37 | imsrv | Productivity | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
38 | inputmethods | UI | MW
39 | ipappprotocols | Data communications | MW
40 | ipappsrv | Personal Comms | MW
41 | ipconnmgmt | Data communications | MW | S^3 | 2009 2H
42 | legacypresence | Productivity | MW
43 | locationsrv | Location | MW
44 | mds | Multimedia | MW
45 | messagingmw | Productivity | MW |  | Proposed
46 | metadatasrv | Multimedia | MW
47 | mmappfw | Multimedia | MW
48 | mmmw | Multimedia | MW
49 | mmuifw | Multimedia | MW
50 | netprotocols | Data communications | MW
51 | networkingdm | Device management | MW
52 | opensrv | Productivity | MW
53 | phonesrv | Personal Comms | MW
54 | remoteconn | Device connectivity | MW
55 | remotemgmt | Device management | MW
56 | remotestorage | Device connectivity | MW
57 | securitysrv | Security | MW
58 | serviceapi | Runtimes | MW
59 | serviceapifw | Runtimes | MW
60 | shortlinkconn | Device connectivity | MW
61 | svgt | UI | MW |  |  | PkO is unaware until now
62 | uiaccelerator | UI | MW |  |  | PkO is unaware until now
63 | uiresources | UI | MW |  |  | PkO is unaware until now
64 | uitools | Tools | MW
65 | usbservices | Device connectivity | MW
66 | videoutils | Multimedia | MW
67 | vpnclient | Data communications | MW
68 | web | Runtimes | MW
69 | websrv | Runtimes | MW
70 | wirelessacc | Data communications | MW | S^3 | 2H/2009

## pending bklog (hidden)
Key? |  | tag
| Wireless_Access/Backlog | Freeway | New Symbian Comms Architecture - A migration to Freeway architecture. |  | 2H/2009 | In development
| Ipappsrv_backlog | NGA | Support for NGA | 2H/2009 | 2H/2009 | In Development.
| Video_Player_Package/Backlog | NGA | Symbian NGA support for video playback Link to feature description | 2009-08-01 | &lt;MCL date&gt; | In development
| VideoTelephony_roadmap | NGA | NGA implemetaion of Video render | 2H/2009 | 2H/2009 | In Development
| Commsfw_Backlog | SMP | SMP | SMP enhanced comms framework | 2010 |  | Proposed
| Graphics_Package/Backlog | SMP | SMP safe - support for multi-core processors |  | 1H/09 (S^3) | In Development
| IP_Connection_Management_Package/Backlog | SMP | Ipconnmgmt SMP-safe: Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Messaging_Package/Backlog | SMP | SMP analysis/ support for messaging |  |  | Proposed
| Vpnclient_Package/Backlog | SMP | SMP safe phase 1 | 2H09 | Planned
| WLAN_Package_Backlog | SMP | SMP safeSupport for multicore processors |  | 2H/09 (SF^3) | Planned
| Wireless_Access/Backlog | SMP | SMP safe verification - Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Access_Security_Package/Backlog | newUI | Implementation of Access Security UIs with Qt | N/A | 2010 1Q | Planned
| Application_Installation_Package/Backlog | newUI | Qt-based AppInstall UI components | Q1 2010 | Q1 2010 | Proposed
| Connectivity_Tools_Package/Backlog | newUI | Qt/Orbit migration for ConnTest | 2H/2009 | 1H/2010 | Proposed
| DRM_Package/Backlog | newUI | Qt-based DRM UI components | Q1 2010 | Q1 2010 | Proposed
yes | IDE_Package/Backlog | newUI | Qt Eclipse integration plugins version 1.5.2 | n/a | Aug 09 | in-progress
| IP_Connection_Management_Package/Backlog | newUI | DirectUI implementation: Orbit implementation of ipconnmgmt UI components. | 2H/2009 | 1H/2010 | Planned
yes | Location_Package/Backlog | newUI | Location UI enhancements with Qt | TBD | TBD | Proposed
yes | Messaging_Package/Backlog | newUI | Conversation based messaging direct touch UI using Qt | 2010-05-01 |  | Ongoing
yes | Phone_backlog | newUI | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | 2H/2009 | 2H/2009 | In Development
yes | Phone_backlog | newUI | Direct UI | 1H/2010 | 1H/2010 | In Development
| Profile_Package/Backlog | newUI | QT'fication of Profiles |  |  | Planned
| Security_Services_Package/Backlog | newUI | Qt-based Securitysrv UI components | Q1 2010 | Q1 2010 | Proposed
yes | VideoTelephony_roadmap | newUI | touch UI support (implementation of common UI API) | 1H/2010 | 1H/2010 | In Development
| Wireless_Access/Backlog | newUI | DirectUI implementation - Orbit (Qt) implementation of wirelessacc UI components. |  | 1H/2010 | Proposed
| Wireless_Access/Backlog | newUI | DirectUI implementation - Replace WLAN Sniffer with Connect Screen. | 2H/2009 | 1H/2010 | Planned