## Integration Plan
BUG_ID | pdk |  | Feature | TAG | S^N | Main Contributor | Package | IW0935 | IW0937 | IW0939 | IW0941 | IW0943 | IW0945 | IW0947 | IW0949 | IW0951 | xmad | IW1003 | IW1005 | IW1007 | IW1009 | IW1011 | IW1013 | 2010-Q2 | 2010-Q3 | 2010-Q4
246-8 | 2.0.0 |  | Additional Kernel components backport for S^3 to S^2 | N/A | S^2 | DOCOMO/SOSCO | Kernel & Hardware Services | IW0939: 0 | [10 empty] | 1
| 3.0.a | -1 | New Comms Framework | 3PC | S^3 | NOKIA | Tech Domain Wide Features | IW0939: 0 | [10 empty] | 1
| 3.0.a | -1 | 3PC architecture | 3PC | S^3 | NOKIA | Comms Framework | IW0939: 0 | [10 empty] | 1
|  |  | SymbianJ | Java | S^3 | NOKIA | SymbianJ | [15 empty] | 1 |  |  |  | 1
1339 |  |  | NFC Server | NFC | S^3 | NOKIA | NFC | [10 empty] | 2 | [8 empty] | 1
1340 |  |  | NFC Lib | NFC | S^3 | NOKIA | NFC | [12 empty] | 2 | [6 empty] | 1
1341 |  |  | NFC Client | NFC | S^3 | NOKIA | NFC | [12 empty] | 2 | [6 empty] | 1
|  |  | TBC | NFC | S^3 | NOKIA | Application packages | [19 empty] | 0
906 |  |  | volume control | AVRCP1.4 | S^3 | NOKIA | Btservices | [19 empty] | 0
1107 |  |  | Browsing | AVRCP1.4 | S^3 | NOKIA | Btservices | [10 empty] | 2 | [8 empty] | 1
1347 |  |  | Single click change | Singletap | S^3 | NOKIA | Files | [10 empty] | 3
1349 |  |  | Contacts single click compatibility | Singletap | S^3 | NOKIA/IXONOS | Contacts | [10 empty] | 3
1345 |  |  | Single Tap in S^3 | Singletap | S^3 | NOKIA | MusicPlayer | IW0951: 3
1348 |  |  | Single Tap changes to Photos app in S^3. | Singletap | S^3 | NOKIA | Photos | IW0951: 3
1368 |  |  | 'Single tap contribution' in Homescreen | Singletap | S^3 | NOKIA | Homescreen
739 |  |  | Sinlge touch | Singletap | S^3 | NOKIA | ClassicUI | IW0947: 2
|  |  | QT 4.6.1 | NewUI | S^3 | NOKIA | QT | IW0951: 2 |  |  |  | 2
266 | ?? |  | Homescreen page switching API | Multipage HS | S^3 | NOKIA | HomeScreen | IW0947: 0 | [10 empty] | 1
267 | ?? |  | Homescreen mode switching API | Multipage HS | S^3 | NOKIA | HomeScreen | IW0947: 0 | [10 empty] | 1
268 | 3.0.d |  | Homescreen page management | Multipage HS | S^3 | NOKIA | HomeScreen | IW0945: 0 | [10 empty] | 1
208 |  |  | CalDav for single calendar | CalDav | S^3 | SUN | Organiser | IW0949: 2 | [10 empty] | 1
496 |  |  | CalDav for Multiple Calendar | CalDav | S^3 | SUN | Organiser | [19 empty] | 0
495 |  |  | Multiple Calendar | CalDav | S^3 | NOKIA | Organiser | [19 empty] | 0
599 |  |  | RT+ Artist and Title support | music store | S^3 | NOKIA | radio app | IW0949: 3 | [10 empty] | 1
600 |  |  | RT+ Web support | music store | S^3 | NOKIA | radio app | IW0949: 3 | [10 empty] | 1
601 |  |  | Music Store support | music store | S^3 | NOKIA | radio app | IW0949: 3 | [10 empty] | 1
565 |  |  | Dialog reduction: A number of connection dialogs are removed from the software for better user experience. | dialog redux | S^3 | NOKIA | ipconmanagement | IW0945: 0; IW0949: 3 | [10 empty] | 2
438 |  |  | Remote contact lookup | lookup | S^3 | NOKIA | Contacts | [12 empty] | 3 | [6 empty] | 1
420 |  |  | Music Playback over HDMI | HDMI | S^3 | NOKIA | Musicplayer | IW0947: 3 | [10 empty] | 1
466 |  |  | Helix engine support for video files > 2GB | 2GB files | S^3 | NOKIA | Helix | IW0949: 3 | [10 empty] | 1
575 | 3.0.d |  | Support for files over 2GB | 2GB files | S^3 | NOKIA | imghandling | IW0945: 0 | [10 empty] | 1
587 | 3.0.d |  | Support for over 2GB files | 2GB files | S^3 | NOKIA | mds | IW0945: 0 | [10 empty] | 1
661 | 3.0.d |  | Local Location Based Triggering Enhancements | LBS | S^3 | NOKIA | Locationserv | IW0945: 0 | [10 empty] | 1
219 | N/A |  | Zoom2 Baseport | ExecEnv | S^3 | TI | BSP | IW0943: 0 | [10 empty] | 1
179 |  |  | NGA adaptation | NGA | S^3 | NOKIA | Telephony Apps | IW0947: 3 | [10 empty] | 1
182 |  |  | Basic Non-NGA Graphic Support | NGA | S^3 | NOKIA | Graphics | IW0939: inFCL | [10 empty] | 1
235 |  | -1 | PC development platform | NGA | S^3 | NOKIA | Graphics | [12 empty] | 1 | [6 empty] | 1
181 |  | -1 | Graphics surfaces and HW acceleration of graphics | NGA | S^3 | NOKIA | Graphics | IW0945: inFCL; IW0951: 3 | [10 empty] | 2
237 |  |  | Widget specific effects | NGA | S^3 | NOKIA | HomeScreen | [19 empty] | 0
238 |  |  | Homescreen background animation | NGA | S^3 | NOKIA | HomeScreen | [19 empty] | 0
245 | 3.0.d |  | Symbian NGA support for video playback Link to feature description | NGA | S^3 | NOKIA | Video player | IW0941: 0 | [10 empty] | 1
578 | 3.0.a |  | SMP prototype Kernel | SMP | S^3 | NOKIA | Kernel & Hardware Services | IW0939: 0 | [10 empty] | 1
579 | 3.0.a |  | Writeable demand paging | WDP | S^3 | NOKIA | Kernel & Hardware Services | IW0939: 0 | [10 empty] | 1
434 |  |  | Contacts application UI revolution using QT | NewUI | S^4 | NOKIA | Contacts | [16 empty] | 3 |  |  | 1
|  |  | TBC | SHAI | S^4 | NOKIA | TBC | [19 empty] | 0
|  |  | Qt-based Start up animation and splash screen | NewUI | S^4 | NOKIA | Generic_Applications_Support | [16 empty] | 3 |  |  | 1
|  |  | Conversation based messaging direct touch UI using Qt | NewUI | S^4 | NOKIA | Messaging | [16 empty] | 3 |  |  | 1
|  |  | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | NewUI | S^4 | NOKIA | Phone | [18 empty] | 3 | 1
|  |  | Direct UI | NewUI | S^4 | NOKIA | Phone | [16 empty] | 3 |  |  | 1
|  |  | touch UI support (implementation of common UI API) | NewUI | S^4 | NOKIA | VideoTelephony | [16 empty] | 3 |  |  | 1
zzz
[6 empty] | Package owner MCL bulk contribution |  | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | Individual Package Contributions
|  |  | IW = integration Window |  | 0 | Done |  | IW0941: 0; IW0943: Planned contribution not recieved or not useable
|  |  | IW is a 2 week cycle at the end produces a PDK |  | 1 | Issue: Late or not committed |  | IW0941: 1; IW0943: Planned contribution in this time frame
[5 empty] | 2 | At risk |  | IW0941: 2; IW0943: Planned contribution recieved
|  |  | BUG_ID - Good engagement with contributor. Timeframe provided |  | 3 | Planned and on track | bar: IW0935 to IW0937
|  |  | BUG_ID - Engagement with contributor is pending |  | InFCL | FCL Drop Available |  | IW0943: -1; IW0945: "Heavy Duty" integration work
|  |  | BUG_ID - too far into the future to start engaging beyond backlog data |  | FCL | FCL Drop planned | bar: IW0935 to IW0937
Note on A18: victorp: we think this has been submitted, but need to confirm with PkO
Note on A19: victorp: pending package backlog. Information provided in conference calls
Note on A23: victorp: impacted by S^3 UI PDK
Note on D34: victorp: recieved information that this has been done, checking with package owner when

## Integration Graph
|  | 1 | 31 | 5
Column Labels
| Values | S^2 | S^3 | S^4 | Grand Total | Values | S^2 | S^3 | S^4
| Count of IW0935 |  |  |  |  | Count of IW0935 | 1 | 31
| Count of IW0937 |  |  |  |  | Count of IW0937 | 1 | 31
| Count of IW0939 | 1 | 5 |  | 6 | Count of IW0939 | 0 | 26
| Count of IW0941 |  | 1 |  | 1 | Count of IW0941 |  | 25
| Count of IW0943 |  | 1 |  | 1 | Count of IW0943 |  | 24
| Count of IW0945 |  | 6 |  | 6 | Count of IW0945 |  | 18
| Count of IW0947 |  | 4 |  | 4 | Count of IW0947 |  | 14
| Count of IW0949 |  | 6 |  | 6 | Count of IW0949 |  | 8
| Count of IW0951 |  | 1 |  | 1 | Count of IW0951 |  | 7
| Count of IW1003 |  | 2 |  | 2 | Count of IW1003 |  | 5
| Count of IW1005 |  |  |  |  | Count of IW1005 |  | 5
| Count of IW1007 |  | 4 |  | 4 | Count of IW1007 |  | 1
| Count of IW1009 |  |  |  |  | Count of IW1009 |  | 1 | 5
| Count of IW1011 |  |  |  |  | Count of IW1011 |  | 1 | 5
| Count of IW1013 |  | 1 |  | 1 | Count of IW1013 |  | 0 | 5
| Count of 2010-Q2 |  |  | 5 | 5 | Count of 2010-Q2 |  |  | 0
| Count of 2010-Q3 |  |  |  |  | Count of 2010-Q3 |  |  | 0
| Count of 2010-Q4 |  |  | 1 | 1
| Non-SMP Safe | SMP SAFE Validated
os | 14 | 9
mw | 38 | 8

## SMP List
| Done |  |  | S^3 Targets
| Still in progress |  |  | S^4 Targets
| Delayed / PkO unaware |  |  | S^5 Targets
| Package | Tech Domain | Layer | SMP Safe in Release | SMP safe Status | Comments
1 | boardsupport | OS Base services | OS | S^3 | Done | Emulator BSP - S^3 validated, HAI - wont be affected by SMP Safe as per PkO
2 | bt | device connectivity | OS | S^3 | Still work in progress | PkO has informed this will be done by wk 52
3 | buildtools | Tools | OS | S^3 | Done | PkO already confirmed this.
4 | cellularsrv | Personal comms | OS | S^3 | Still work in progress | Except for CTSY, PkO aims to complete this by Q4
5 | commsfw | Data communication | OS | S^3 | Done | PkO already confirmed this.
6 | deviceplatformrelease | Device Management | OS | S^3 | N/A | As per William Robert, SMP Safe may not apply for this package as its on the host side.
7 | devicesrv | OS Base services | OS | S^3 | Still work in progress | SW components validated for S^3, HW components pending. Timeframe to be made available shortly. 4th Nov: PkO has written that h/w validation is targeted only by Q2/2010. Have asked for further clarification and notified about TB9.2 deadline. 16th Nov: PkO has been referred to MH/Nokia for h/w testing.
8 | graphics | UI | OS | S^3 | Done | Faisal Memon, the new PkO has already confirmed this.
9 | imagingext | Multimedia | OS | S^3 | Still work in progress | PkO aims to complete this by wk 48
10 | kernelhwsrv | OS Base services | OS | S^3 | Done | PkO already confirmed this.
11 | lbs | Location | OS | S^3 | Done | PkO already confirmed this.
12 | mm | Multimedia | OS | S^3 | Done | PkO already confirmed this.
13 | networkingsrv | Data communication | OS | S^3 | 90% test cases done | PkO has responded to ensure 100% within S^3
14 | osrndtools | Tools | OS | S^3 | Still work in progress | PkO aims to complete this by Q4/2009
15 | ossrv | openservices???? | OS | S^3 | Still work in progress | Its been agreed that this is still a Wk 52 2009 target. | written kirill anyway...
16 | persistentdata | OS Base services | OS | S^3 | Done | PkO already confirmed this.
17 | security | security | OS | S^3 | Done | Pko already confirmed this.
18 | shortlinksrv | device connectivity | OS | S^3 | Still work in progress | Pko aims to complete this by Q4/2009
19 | text andloc | UI | OS | S^3 | Still work in progress | PkO aims to complete this by wk48
20 | unref |  | OS | S^3 | N/A | This is not a package, but code shared across multiple packages. No SMP related testing needs to be done for this as a 'package'.
21 | usb | device connectivity | OS | S^3 | Still work in progress | Pko aims to complete this by wk46
22 | wlan | Data communication | OS | S^3 | Still work in progress | PkO expects this to get over by week 48
23 | xmlsrv | Runtimes | OS | S^3 | Still work in progress | xmlsecurityengine is pending . PkO has assured validation before Q4/2009
24 | accesssec | Data communications | MW | S^4 | Still work in progress | Q1/2010
25 | appinstall | Runtimes | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
26 | appsupport |  | MW | S^3 | Still work in progress | PkO expects this to get over by week 50
27 | btservices | Device connectivity | MW | S^3 | Still work in progress | PkO owner aims to achieve this by week 52
28 | camerasrv | Multimedia applications | MW | S^4 |  | PkO is unaware until now. Hasnt responded to reminders, Nov 17th : Written about the SMP proposal and referred to Mark Hambleton.
29 | classicui | UI | MW | S^4 |  | PkO is unaware until now. Hasnt responded to reminders. Nov 17th : Steven Yao-PkO has asked for H/W to validate. Have referred to MH/Nokia.
30 | dlnasrv | Device connectivity | MW | S^4 |  | PkO confirms this to be a S^4 target
31 | drm | Security | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
32 | gsprofilesrv |  | MW | S^4 |  | PkO confirms this to be a S^4 target
33 | hapticsservices | UI | MW | S^4 |  | PkO is unaware until now.
34 | helix | ?????? | MW | S^3 | Still work in progress | PkO expects this to get over by week 50
35 | homescreensrv | UI | MW | S^3 | Still work in progress | PkO reckons this package wont be affected by SMP plans. Awaiting confirmation
36 | imghandling | Multimedia | MW | S^3 | Done | PkO has confirmed this
37 | imsrv | Productivity | MW | S^3 | Still work in progress | PkO expects this to get over by week 47
38 | inputmethods | UI | MW | S^4 | Still work in progress | Pko expects this to be a S^4 target, timelines unknown. Response sought from PkO.
39 | ipappprotocols | Data communications | MW | S^3 | Done | PkO has confirmed this
40 | ipappsrv | Personal Comms | MW | S^4 |  | Pko is unaware until now, has been referred to the proposal.
41 | ipconnmgmt | Data communications | MW | S^4 | Still work in progress | Pko unwilling to commit dates, expects this to get over by Q1 2010
42 | legacypresence | Productivity | MW | S^4 |  | PkO has ruled out S^3, tentative on S^4. Confirmation awaited.
43 | locationsrv | Location | MW | S^3 | Still work in progress | Pko expects this to get over by wk52
44 | mds | Multimedia | MW | S^3 | Done | Done
45 | messagingmw | Productivity | MW |  |  | PkO identified and contacted, 5th Nov - reminder sent.
46 | metadatasrv | Multimedia | MW | S^3 | Done | Pko has already confirmed this
47 | mmappfw | Multimedia | MW | S^4 | Still work in progress | Pko has no specific time frame info
48 | mmmw | Multimedia | MW |  |  | Pko has been contacted again... No update yet.
49 | mmuifw | Multimedia | MW | S^4 |  | Pko unaware of SMP plans, have referred to proposal doc. Response awaited. Reminders sent once again.
50 | netprotocols | Data communications | MW | S^3 | Done | PkO has confirmed this
51 | networkingdm | Device management | MW | S^3 | Done | PkO has confirmed this
52 | opensrv | Productivity | MW |  |  | PkO has promised to come back next week
53 | phonesrv | Personal Comms | MW |  |  | PkO sent reminder once again
54 | remoteconn | Device connectivity | MW | S^4 | Still work in progress | Week 48
55 | remotemgmt | Device management | MW | S^3 | Still work in progress | PkO aims to complete this by H2/2009
56 | remotestorage | Device connectivity | MW | S^4 | Still work in progress | Week 48
57 | securitysrv | Security | MW | S^3 | Done | PkO has confirmed this
58 | srvdiscovery |  | MW | S^4 | Still work in progress | Pko expects this to happen by week 48 and on TB 10.1
59 | platformtools |  | MW
60 | shortlinkconn | Device connectivity | MW
61 | svgt | UI | MW | S^4 |  | PkO is unaware until now, pinged for feedback again
62 | uiaccelerator | UI | MW | S^4 |  | PkO is unaware until now, pinged for feedback again
63 | uiresources | UI | MW | S^4 |  | PkO is unaware until now. Hasnt responded to reminders. Nov 17th : Steven Yao-PkO has asked for H/W to validate. Have referred to MH/Nokia.
64 | uitools | Tools | MW | S^3 | Done / not required. Windows / Linux tools | PkO confirms all this to be Linux / Windows tools and hence not necessary to be SMP Safe.
65 | usbservices | Device connectivity | MW | S^3 | Still work in progress | Pko aims this to be Week 46/09 target
66 | videoutils | Multimedia | MW |  |  | Pko unaware of SMP plans, have referred to proposal doc.
67 | vpnclient | Data communications | MW | S^3 | Still work in progress | PkO aims to complete this by Q4/2009
68 | websrv | Runtimes | MW | S^3 | Done | PkO confirms this and SMP Safe code to be made available as early as week 45
69 | wirelessacc | Data communications | MW | S^3 | 2H/2009 | PkO yet to confirm.. Response awaited.
70 | devicectrl |  | APP | S^3 | Still work in progress | Pko expects this to happen by Q4/2009
71 | commonemail |  | APP |  |  | Pko contacted. Response awaited
72 | camera |  | APP |  |  | Pko contacted. Response awaited
73 | conntools |  | APP |  |  | Pko contacted. Response awaited
74 | contacts |  | APP | S^4 | work in progress | PKO confirms this is wk18/2010 target
75 | contentcontrol |  | APP | S^4 | work in progress | PkO will provide details on schedule eventually
76 | conversations |  | APP |  |  | Pko contacted. Response awaited
77 | devicecontrol |  | APP |  |  | Pko contacted. Response awaited
78 | dictionary |  | APP |  |  | Pko contacted. Response awaited
79 | files |  | APP |  |  | Pko contacted. Response awaited
80 | gallery |  | APP |  |  | Pko contacted. Response awaited
81 | graphicsuis |  | APP |  |  | Pko contacted. Response awaited
82 | helps |  | APP |  |  | Pko contacted. Response awaited
83 | homescreen |  | APP |  |  | Pko contacted. Response awaited
84 | homescreentools |  | APP |  |  | Pko contacted. Response awaited
85 | im |  | APP |  |  | Pko contacted. Response awaited
86 | imgeditor |  | APP |  |  | Pko contacted. Response awaited
87 | imgvieweruis |  | APP |  |  | Pko contacted. Response awaited
88 | iptelephony |  | APP |  |  | Pko contacted. Response awaited
89 | java |  | APP | S^4 |  | PkO will provide details on schedule eventually
90 | speechsrv |  | APP | S^4 | work in progress, lot of work anticipated | PkO will provide details on schedule eventually
91 | settingsuis |  | APP | S^4 | work in progress | targeted for Q2/2010
92 | utils |  | APP | S^4 | work in progress
93 | musicplayer |  | APP | S^4 | work in progress
94 | voicerec |  | APP | S^4 | work in progress
95 | printing |  | APP | S^5 | work in progress | Target is too far away to provide deadlines
96 | messaging |  | APP | S^4 | work in progress

## pending bklog (hidden)
Key? |  | tag
| Wireless_Access/Backlog | Freeway | New Symbian Comms Architecture - A migration to Freeway architecture. |  | 2H/2009 | In development
| Ipappsrv_backlog | NGA | Support for NGA | 2H/2009 | 2H/2009 | In Development.
| Video_Player_Package/Backlog | NGA | Symbian NGA support for video playback Link to feature description | 2009-08-01 | &lt;MCL date&gt; | In development
| VideoTelephony_roadmap | NGA | NGA implemetaion of Video render | 2H/2009 | 2H/2009 | In Development
| Commsfw_Backlog | SMP | SMP | SMP enhanced comms framework | 2010 |  | Proposed
| Graphics_Package/Backlog | SMP | SMP safe - support for multi-core processors |  | 1H/09 (S^3) | In Development
| IP_Connection_Management_Package/Backlog | SMP | Ipconnmgmt SMP-safe: Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Messaging_Package/Backlog | SMP | SMP analysis/ support for messaging |  |  | Proposed
| Vpnclient_Package/Backlog | SMP | SMP safe phase 1 | 2H09 | Planned
| WLAN_Package_Backlog | SMP | SMP safeSupport for multicore processors |  | 2H/09 (SF^3) | Planned
| Wireless_Access/Backlog | SMP | SMP safe verification - Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Access_Security_Package/Backlog | newUI | Implementation of Access Security UIs with Qt | N/A | 2010 1Q | Planned
| Application_Installation_Package/Backlog | newUI | Qt-based AppInstall UI components | Q1 2010 | Q1 2010 | Proposed
| Connectivity_Tools_Package/Backlog | newUI | Qt/Orbit migration for ConnTest | 2H/2009 | 1H/2010 | Proposed
| DRM_Package/Backlog | newUI | Qt-based DRM UI components | Q1 2010 | Q1 2010 | Proposed
yes | IDE_Package/Backlog | newUI | Qt Eclipse integration plugins version 1.5.2 | n/a | Aug 09 | in-progress
| IP_Connection_Management_Package/Backlog | newUI | DirectUI implementation: Orbit implementation of ipconnmgmt UI components. | 2H/2009 | 1H/2010 | Planned
yes | Location_Package/Backlog | newUI | Location UI enhancements with Qt | TBD | TBD | Proposed
yes | Messaging_Package/Backlog | newUI | Conversation based messaging direct touch UI using Qt | 2010-05-01 |  | Ongoing
yes | Phone_backlog | newUI | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | 2H/2009 | 2H/2009 | In Development
yes | Phone_backlog | newUI | Direct UI | 1H/2010 | 1H/2010 | In Development
| Profile_Package/Backlog | newUI | QT'fication of Profiles |  |  | Planned
| Security_Services_Package/Backlog | newUI | Qt-based Securitysrv UI components | Q1 2010 | Q1 2010 | Proposed
yes | VideoTelephony_roadmap | newUI | touch UI support (implementation of common UI API) | 1H/2010 | 1H/2010 | In Development
| Wireless_Access/Backlog | newUI | DirectUI implementation - Orbit (Qt) implementation of wirelessacc UI components. |  | 1H/2010 | Proposed
| Wireless_Access/Backlog | newUI | DirectUI implementation - Replace WLAN Sniffer with Connect Screen. | 2H/2009 | 1H/2010 | Planned

## pdk3.0.d (hidden)
BUG ID | Title | KF | Contrib | Package
575 | Support for files over 2GB | 2GB files | NOKIA | imghandling
587 | Support for over 2GB files | 2GB files | NOKIA | mds
661 | Local Location Based Triggering Enhancements | LBS | NOKIA | Locationserv
245 | Symbian NGA support for video playback Link to feature description | NGA | NOKIA | Video player
268 | Homescreen page management | Multipage HS | NOKIA | HomeScreen
Note on B3: victorp: recieved information that this has been done, checking with package owner when