## Integration Plan
BUG_ID | pdk |  | Feature | TAG | S^N | Main Contributor | Package | IW0935 | IW0937 | IW0939 | IW0941 | IW0943 | IW0945 | IW0947 | IW0949 | IW0953 | xmas | IW1003 | IW1005 | IW1007 | IW1009 | IW1011 | IW1013 | IW1015 | IW1017 | IW1019 | IW1021 | IW1023 | IW1025 | IW1027 | IW1029 | IW1031 | IW1033 | IW1035 | IW1037 | IW1039 | 2010-Q4 | 2011-Q1
246-8 | 2.0.0 |  | Additional Kernel components backport for S^3 to S^2 | N/A | S^2 | DOCOMO/SOSCO | Kernel & Hardware Services |  |  | 0 | [28 empty] | 1
| 3.0.a | -1 | New Comms Framework | 3PC | S^3 | NOKIA | Tech Domain Wide Features |  |  | 0 | [28 empty] | 1
| 3.0.a | -1 | 3PC architecture | 3PC | S^3 | NOKIA | Comms Framework |  |  | 0 | [28 empty] | 1
|  |  | SymbianJ | Java | S^3 | NOKIA | SymbianJ | [15 empty] | 1 | [15 empty] | 1
1339 |  |  | NFC Server | NFC | S^5 | NOKIA | NFC | [31 empty] | 0
1340 |  |  | NFC Lib | NFC | S^5 | NOKIA | NFC | [31 empty] | 0
1341 |  |  | NFC Client | NFC | S^5 | NOKIA | NFC | [31 empty] | 0
906 | 3.0.f |  | volume control | AVRCP1.4 | S^3 | NOKIA | Btservices | [10 empty] | 0 | [20 empty] | 1
1347 | 3.0.f |  | Single click change | Singletap | S^3 | NOKIA | Files | [10 empty] | 0
1349 | 3.0.f |  | Contacts single click compatibility | Singletap | S^3 | NOKIA/IXONOS | Contacts | [8 empty] | 0
1345 | 3.0.f |  | Single Tap in S^3 | Singletap | S^3 | NOKIA | MusicPlayer | [8 empty] | 0
1348 | 3.0.f |  | Single Tap changes to Photos app in S^3. | Singletap | S^3 | NOKIA | Photos | [8 empty] | 0
1368 | 3.0.f |  | 'Single tap contribution' in Homescreen | Singletap | S^3 | NOKIA | Homescreen | [7 empty] | 0
1464 | 3.0.f |  | Single tap in organiser | Singletap | S^3 | NOKIA | Organiser | [7 empty] | 0
1397 | ?? |  | Single Tap in S^3 - Email UI | Singletap | S^3 | NOKIA | commonemail | [13 empty] | 0
739 | 3.0.f |  | Sinlge touch | Singletap | S^3 | NOKIA | ClassicUI | [7 empty] | 0
1451 | N/a |  | Make Qt 4.6.0 available to SF | NewUI | S^3 | NOKIA | QT | [8 empty] | 0
1468 | ?? |  | Make QT 4.6.1 available to SF | NewUI | S^3 | NOKIA | QT | [14 empty] | 0
266 | 3.0.e |  | Homescreen page switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [24 empty] | 1
267 | 3.0.e |  | Homescreen mode switching API | Multipage HS | S^3 | NOKIA | HomeScreen | [6 empty] | 0 | [24 empty] | 1
268 | 3.0.d |  | Homescreen page management | Multipage HS | S^3 | NOKIA | HomeScreen | [5 empty] | 0 | [25 empty] | 1
208 | 3.0.g |  | CalDav for single calendar | CalDav | S^3 | SUN | Organiser | [11 empty] | 0 | [19 empty] | 1
496 | 3.0.g |  | CalDav for Multiple Calendar | CalDav | S^3 | SUN | Organiser | [11 empty] | 0 | [19 empty] | 1
495 | 3.0.g |  | Multiple Calendar | CalDav | S^3 | NOKIA | Organiser | [11 empty] | 0 | [19 empty] | 1
599 | 3.0.f |  | RT+ Artist and Title support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [23 empty] | 1
600 | 3.0.f |  | RT+ Web support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [23 empty] | 1
601 | 3.0.f |  | Music Store support | music store | S^3 | NOKIA | radio app | [7 empty] | 0 | [23 empty] | 1
565 | 3.0.e |  | Dialog reduction: A number of connection dialogs are removed from the software for better user experience. | dialog redux | S^3 | NOKIA | ipconmanagement | [5 empty] | 0 |  | 0 | [23 empty] | 2
438 | 3.0.f |  | Remote contact lookup | lookup | S^3 | NOKIA | Contacts | [8 empty] | 0 | [22 empty] | 1
420 | ?? |  | Music Playback over HDMI | HDMI | S^3 | NOKIA | Musicplayer | [14 empty] | 0 | [16 empty] | 1
466 | 3.0.f |  | Helix engine support for video files > 2GB | 2GB files | S^3 | NOKIA | Helix | [8 empty] | 0 | [22 empty] | 1
575 | 3.0.d |  | Support for files over 2GB | 2GB files | S^3 | NOKIA | imghandling | [5 empty] | 0 | [25 empty] | 1
587 | 3.0.d |  | Support for over 2GB files | 2GB files | S^3 | NOKIA | mds | [5 empty] | 0 | [25 empty] | 1
661 | 3.0.d |  | Local Location Based Triggering Enhancements | LBS | S^3 | NOKIA | Locationserv | [5 empty] | 0 | [25 empty] | 1
219 | N/A |  | Zoom2 Baseport | ExecEnv | S^3 | TI | BSP |  |  |  |  | 0 | [26 empty] | 1
179 | 3.0.d |  | NGA adaptation | NGA | S^3 | NOKIA | Telephony Apps | [5 empty] | 0 | [25 empty] | 1
182 | N/A |  | Basic Non-NGA Graphic Support | NGA | S^3 | NOKIA | Graphics |  |  | inFCL | [28 empty] | 1
235 |  | -1 | PC development platform | NGA | S^4 | NOKIA | Graphics | [31 empty] | 0
181 | 3.0.f | -1 | Graphics surfaces and HW acceleration of graphics | NGA | S^3 | NOKIA | Graphics | [5 empty] | inFCL |  |  |  |  | 0 | [20 empty] | 2
1391 | 3.0.g |  | UI Acceleration migration to OpenWF | NGA | S^3 | NOKIA | UIaccelerator | [11 empty] | 0
237 |  |  | Widget specific effects | NGA | S^3 | NOKIA | HomeScreen | [31 empty] | 0
238 | 3.0.f |  | Homescreen background animation | NGA | S^3 | NOKIA | UIaccelerator | [8 empty] | 0 | [22 empty] | 1
245 | 3.0.d |  | Symbian NGA support for video playback Link to feature description | NGA | S^3 | NOKIA | Video player |  |  |  | 0 | [27 empty] | 1
578 | 3.0.a |  | SMP prototype Kernel | SMP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [28 empty] | 1
579 | 3.0.a |  | Writeable demand paging | WDP | S^3 | NOKIA | Kernel & Hardware Services |  |  | 0 | [28 empty] | 1
434 |  |  | Contacts application UI revolution using QT | DirectUI | S^4 | NOKIA | Contacts | [24 empty] | 0 | [6 empty] | 1
1470 |  | -1 | Make Qt 4.7 available for Symbian Foundation | DirectUI | S^4 | NOKIA | QT | [28 empty] | 3
|  | -1 | Orbit | DirectUI | S^4 | NOKIA | Uiemo
658 |  |  | Qt Location UI Apps | DirectUI | S^4 | NOKIA | Location
624 |  |  | Conversation based messaging direct touch UI using Qt | DirectUI | S^4 | NOKIA | Messaging
702 |  |  | Implementation of Access Security UIs with Qt | DirectUI | S^4 | NOKIA | accesssec | [20 empty] | 0
560 |  |  | Qt-based Start up animation and splash screen | DirectUI | S^4 | NOKIA | Generic_Applications_Support | [28 empty] | 3 |  |  | 1
826 |  |  | Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 0 | [14 empty] | 1
703 |  |  | Deprecation of EAP DB platform APIs and implementation of a new Qt EAP configuration API | DirectUI | S^4 | NOKIA | accesssec | [20 empty] | 0
1242 |  |  | Handle UI based on UX Gen2 spec | DirectUI | S^4 | NOKIA | InternetRadio | [18 empty] | 0
1510 |  |  | New input UI and framework on QT | DirectUI | S^4 | NOKIA | inputmethods | [28 empty] | 3
1949 |  |  | Direct UI support for Email | DirectUI | S^4 | NOKIA | commonemail | [28 empty] | 3
1986 |  |  | Migrating to Qt | DirectUI | S^4 | Ixonos | Video editor
602 |  |  | QT and Orbit-based Views | DirectUI | S^4 | NOKIA | radio app
1425 |  |  | Qt UI of Video Telephony | DirectUI | S^4 | NOKIA | Videotelephony | [20 empty] | 0
1572 |  |  | New setting plug-ins for QT version Control panel | DirectUI | S^4 | NOKIA | SettingUI | [28 empty] | 3
1528 |  |  | Homescreen:Basic Orbit based Homescreen | DirectUI | S^4 | NOKIA | Homescreen | [23 empty] | 0
1842 |  |  | Basic MO and MT call features with Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 0
1845 |  |  | Dialer support with Direct UI | DirectUI | S^4 | NOKIA | Phone | [16 empty] | 0
1874 |  |  | Common UI for CS videotelphony and VideoSharing with Direct UI | DirectUI | S^4 | NOKIA | mmsharinguis | [17 empty] | 0
1880 |  |  | Remove all AVKON dependencies | DirectUI | S^4 | NOKIA | iptelephony | [16 empty] | 0
1881 |  |  | VoIP MO and MT call supoprt with Direct UI | DirectUI | S^4 | NOKIA | phone | [29 empty] | 3
1946 |  | -1 | deprecate the emulator | DirectUI | S^4 | NOKIA | Kernel | [18 empty] | 0
2031 |  |  | Basic Direct UI Camera Application | DirectUI | S^4 | NOKIA | Camera | [18 empty] | 0
2048 |  |  | Photos Direct UI implementation using Qt based Orbit library | DirectUI | S^4 | NOKIA | photos | [18 empty] | 0
1588 |  |  | Videoplayer Direct UI implementation using Qt based Orbit library for Symbian^4. | DirectUI | S^4 | NOKIA | Video player | [28 empty] | 1
1110 |  |  | Direct UI support for Bluetooth UI and Bluetooth UI implementation renovation | DirectUI | S^4 | NOKIA | BT services | [28 empty] | 3
2216 |  |  | Migrate new Printing framework UI to Qt | DirectUI | S^4 | NOKIA | Printing
2078 |  |  | DirectUI support for Calendar, Clock and Notes | DirectUI | S^4 | NOKIA | Organizer
2040 |  |  | Image and video quality setting for Direct UI Camera application | DirectUI | S^4 | NOKIA | Camera | [18 empty] | 0
546 |  |  | SMP Safe (support for multicore processors) |  | S^4 | NOKIA | wlan | [28 empty] | 3
701 |  |  | Support for Parallel Processing in Multicore processors |  | S^4 | NOKIA | AccessSec | [28 empty] | 3
3093 |  |  | Direct UI based application | DirectUI | S^4 | NOKIA | InternetRadio
3094 |  |  | Direct UI based application | DirectUI | S^4 | NOKIA | MusicPlayer
3097 |  |  | Direct UI based application | DirectUI | S^4 | NOKIA | IPTelephony | [23 empty] | 0
3098 |  |  | Direct UI based application | DirectUI | S^4 | NOKIA | conversations
2740 |  |  | SMP Product Quality kernel |  | S^4 | NOKIA | Kernel | [28 empty] | 3
2041 |  |  | Exposure and color settings for Direct UI Camera application | DirectUI | S^4 | NOKIA | Camera | [18 empty] | 0
zzz
[6 empty] | Package owner MCL bulk contribution |  | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 2 |  | 2 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | Individual Package Contributions
|  |  | IW = integration Window |  | 0 | Done | [8 empty] | 0 | Planned contribution not recieved or not useable
|  |  | IW is a 2 week cycle at the end produces a PDK |  | 1 | Issue: Late or not committed | [8 empty] | 1 | Planned contribution in this time frame
[5 empty] | 2 | At risk | [8 empty] | 2 | Planned contribution recieved
|  |  | BUG_ID - Good engagement with contributor. Timeframe provided |  | 3 | Planned and on track
|  |  | BUG_ID - Engagement with contributor is pending |  | InFCL | FCL Drop Available | [9 empty] | -1 | "Heavy Duty" integration work
|  |  | BUG_ID - too far into the future to start engaging beyond backlog data |  | FCL | FCL Drop planned
Note on S32: victorp: delivery date moved by 2 month
Note on U32: victorp: slip again, in test phase but no clear plan for delivery
Note on D35: victorp: recieved information that this has been done, checking with package owner when
Note on S41: victorp: Not all code in the FCL has made it to the MCL , possible distributionpolicy error in delivery
Note on AF82: Symbian Foundation: Feature development invalid in S^4

## Integration Graph
28
Column Labels
| Values | S^4 | Grand Total |  | Values | S^4
| Count of IW1015 | 4 | 4 |  | Count of IW1015 | 24
| Count of IW1017 | 1 | 1 |  | Count of IW1017 | 23
| Count of IW1019 | 6 | 6 |  | Count of IW1019 | 17
| Count of IW1021 |  |  |  | Count of IW1021 | 17
| Count of IW1023 | 3 | 3 |  | Count of IW1023 | 14
| Count of IW1025 |  |  |  | Count of IW1025 | 14
| Count of IW1027 |  |  |  | Count of IW1027 | 14
| Count of IW1029 | 2 | 2 |  | Count of IW1029 | 12
| Count of IW1031 | 1 | 1 |  | Count of IW1031 | 11
| Count of IW1033 |  |  |  | Count of IW1033 | 11
| Count of IW1035 |  |  |  | Count of IW1035 | 11
| Count of IW1037 |  |  |  | Count of IW1037 | 11
| Count of IW1039 | 10 | 10 |  | Count of IW1039 | 1
| Count of 2010-Q4 | 1 | 1 |  | Count of 2010-Q4 | 0
|  | 1 | 41 | 42
Column Labels
| Values | S^2 | S^3 | Grand Total |  |  | Values | S^2 | S^3 | Grand Total
| Count of IW0935 | [5 empty] | Count of IW0935 | 1 | 41
| Count of IW0937 | [5 empty] | Count of IW0937 | 1 | 41
| Count of IW0939 | 1 | 5 | 6 |  |  | Count of IW0939 | 0 | 36
| Count of IW0941 |  | 1 | 1 |  |  | Count of IW0941 |  | 35
| Count of IW0943 |  | 1 | 1 |  |  | Count of IW0943 |  | 34
| Count of IW0945 |  | 7 | 7 |  |  | Count of IW0945 |  | 27
| Count of IW0947 |  | 2 | 2 |  |  | Count of IW0947 |  | 25
| Count of IW0949 |  | 7 | 7 |  |  | Count of IW0949 |  | 18
| Count of IW0953 |  | 7 | 7 |  |  | Count of IW0953 |  | 11
| Count of IW1003 |  | 3 | 3 |  |  | Count of IW1003 |  | 8
| Count of IW1005 |  | 4 | 4 |  |  | Count of IW1005 |  | 4
| Count of IW1007 | [5 empty] | Count of IW1007 |  | 4
| Count of IW1009 |  | 1 | 1 |  |  | Count of IW1009 |  | 3
| Count of IW1011 |  | 2 | 2 |  |  | Count of IW1011 |  | 1
| Count of IW1013 |  | 1 | 1 |  |  | Count of IW1013 |  | 0
| Count of 2010-Q4 | [5 empty] | Count of 2010-Q4
0
| Non-SMP Safe SW | SMP SAFE SW Validated | Count N/A
os | 1 | 20 | 2 |  | 23
mw | 15 | 18 | 17 |  | 50
| Non-SMP Safe HW | SMP SAFE HW Validated | Count N/A
os | 5 | 14 | 4 |  | 23
mw | 31 | 10 | 9 |  | 50
OS | SW | HW
safe | 20 | 14
non-safe | 1 | 5
mw | SW&HW
safe | 18
non-safe | 15

## SMP List
| Done |  |  | S^3 Targets
| Still in progress |  |  | S^4 Targets
| Delayed / PkO unaware |  |  | S^5 Targets
SMP safe Status
| Package | Tech Domain | Layer | SMP Safe in Release | S/w based validation (Crazy scheduler) | H/w based validation (naviengine / bridge) | PkO name | Comments
1 | boardsupport | OS Base services | OS | S^3 | Done | n/a |  | Emulator BSP - SMP validated for S^3, HAI - wont be affected by SMP Safe as per PkO
2 | buildtools | Tools | OS | S^3 | Done | n/a |  | Build tools are host side and hence h/w testing is not applicable.
3 | cellularsrv | Personal comms | OS | S^3 | Done | Delayed | Nithin Vijay | PkO unable to provide any commitments on completion
4 | commsfw | Data communications | OS | S^3 | Done | Done |  | PkO already confirmed this.
5 | deviceplatformrelease | Device Management | OS | S^3 | n/a | n/a | Sampo Savoleinen | As per William Robert, SMP Safe may not apply for this package as its on the host side.
6 | devicesrv | OS Base services | OS | S^3 | Done | Done | Arun Varghese | Wk 35: PkO updates that this activity is now complete
7 | graphics | UI | OS | S^3 | Done | Done |  | Faisal Memon, the new PkO has already confirmed this.
8 | imagingext | Multimedia | OS | S^3 | Done | Delayed | Pranav Mishra | PkO aims to complete this by wk 48, Wk 50: Asked for updates from package owners, updates are coming by for individual components. Have asked PkO to respond for the comp package. PkO has promised to come back by end of week 50. week 51: only one component validation pending - jan 4th week target, wk 6: Have written Pranav Mishra again. wk 8: Updates are coming in parts. However, for some of the components only . emulator based testing has been done. wk 11: pinged pko for update - update pending still. wk 32: Discussions planned due to package reorganisation.
9 | kernelhwsrv | OS Base services | OS | S^3 | Done | Done |  | PkO already confirmed this.
10 | lbs | Location | OS | S^3 | Done | Done | Billy Gibson | PkO already confirmed this.
11 | mm | Multimedia | OS | S^3 | Done | Done | Jeremy Murray Wakefield | PkO already confirmed this.
12 | networkingsrv | Data communications | OS | S^3 | Done | Done |  | PkO has responded to ensure 100% within S^3, wk 51: PkO has confirmed this
13 | osrndtools | Tools | OS | S^3 | Done | Done |  | PkO aims to complete this by Q4/2009, wk2: No updates from PkO yet. Wk 6: Pinged Matti Laitinen for an update.
14 | ossrv | OS Base services | OS | S^3 | Done | Done |  | Its been agreed that this is still a Wk 52 2009 target. Wk 51: PkO has confirmed this now.
15 | persistentdata | OS Base services | OS | S^3 | Done | Done |  | PkO already confirmed this. | written kirill anyway...
16 | OS Security | Security | OS | S^3 | Done | Done | Santosh Patil | Pko already confirmed this.
17 | bt(was part of shortlinksrv) | Device connectivity | OS | S^3 | Done | Done |  | Pko aims to complete this by Q4/2009 wk2: PkO still validating. Wk 6: Pinged Pko for confirmation
18 | usb (was part of shortlinksrv) | Device connectivity | OS | S^3 | Done | Delayed until wk 44 | Xialong Shi | Wk16: Now planned for Wk 44
19 | NFC (new pk add into shortlinksrv) |  | OS | S^4 |  |  | Mikko Saarisalo | wk 50: Have contacted Mikko. Response awaited
20 | textandloc | UI | OS | S^3 | Done | Done |  | PkO aims to complete this by wk48: Wk 50: Asked for updates from package owners, wk51: Pinged pko again. Change in PkO. No response yet.
21 | unref |  | OS | S^3 | n/a | n/a |  | This is not a package, but code shared across multiple packages. No SMP related testing needs to be done for this as 'package' using the code will be validated anyway.
22 | wlan | Data communications | OS | S^3 | Done | Delayed | Arto Suomi | PkO expects this to get over by week 48. Wk: 50: PkO confirms that crazy scheduler based validation is now over. Hw based testing is only planned for spring 2010. Wk 51: Have informed pko about early feb 2010 for S^3 deadline. Wk 7: Package owner confirms lack of hardware. wk 32: PkO still has hardware issues
23 | xmlsrv | Runtimes | OS | S^3 | Done | Done | Rashmi Kumar | xmlsecurityengine is pending . PkO has assured validation before Q4/2009. Wk 51: Pinged Pko for a response. Only one component is pending. Wk 51: PkO has confirmed
24 | accesssec | Data communications | MW | S^4 | Still work in progress |  |  | Wk 18 update : H1 2010
25 | appinstall | Runtimes | MW | S^3 | Done | Done | Timo Heikkinen | PkO expects this to get over by week 47. Wk 50: have asked for updates. Wk51: Software based validation done. Hw based validation pending. Wk 6: Done Done
26 | appsupport | Runtimes | MW | S^3 | Still work in progress |  | Subani Basha | PkO expects this to get over by week 50. wk51: Contacted pko for a response. Wk2: pinged Subani (pko) again, wk 11: pinged again
27 | btservices | Device connectivity | MW | S^3 | Done | wk 26 |  | PkO owner aims to achieve this by week 52. wk2: Pinged sander again for a response.
28 | camerasrv | Multimedia applications | MW | S^4 |  |  | Teemu Rossi | PkO is unaware until now. Hasnt responded to reminders, Nov 17th : Written about the SMP proposal and referred to Mark Hambleton. Wk 50: Pko will get back next week. Wk51: Pinged package owner again. Wk 6: written teemu on S^4 targets. wk7: Teemu has no SMP requirements on his backlog
29 | classicui | UI | MW | S^4 | n/a | n/a |  | PkO is unaware until now. Hasnt responded to reminders. Wk 51: Pk will be deprecated from S^4
30 | dlnasrv | Device connectivity | MW | S^4 | n/a | n/a |  | Wk 16: Pk may not be part of S^4.
31 | DRM | Security | MW | S^3 | Still work in progress |  | Simo Jarvinen | PkO expects this to get over by week 47: wk 50 - have asked pko for status wk51: Pko confirms crazy scheduler based validation nearly complete. Hw based validation pending. Wk2: Written a mail to Simo wk 4, wk 8: no response from PkO, wk 11: pinged again
32 | gsprofilesrv | Device Management | MW | S^4 | wk 26 |  | Wang xiaoyun | Wk 16: PkO confirms wk 26 target
33 | hapticsservices | UI | MW | S^4 |  |  | Steven Yao | PkO is unaware until now. Wk47: Referred to MH/ Nokia for plans. Wk 51: Have contacted for plans/progress/status. Wk2: reminded package owner.. Wk 6: PkO is still 'unaware of SMP' plans !!!
34 | helix | Multimedia | MW | S^4 | Done | No access to hardware | Junhong Liu | Wk 16: No access to hardware and hence no commits on deadline.
35 | homescreensrv | UI | MW | S^4 | still work in progress | wk51: Was S^3 earlier, now targeted for S^4 |  | PkO reckons this package wont be affected by SMP plans. Wk51: PkO has confirmed this package is now targeted for S^4 and not S^3. Validation plans, if any, are being worked out. Wk 5: now rescheduled to S^4
36 | imghandling | Multimedia | MW | S^3 | Done | No access to hardware, timeframes unknown | Henri Autio | Wk 16: No access to hardware and hence no commits on deadline.
37 | imsrv | Productivity | MW | S^3 | Still work in progress | No access to hardware | Shrikumar B Sharma | PkO expects this to get over by week 47, wk 50: have asked pko for status, wk51: Sent a reminder again, wk2: have pinged Pko wk 7: pinged again, wk 11: pinged again
38 | inputmethods | UI | MW | S^4 |  |  | Antti M Seppala | Wk 16: PkO has no SMP plans. Further discussions in progress.
39 | ipappprotocols | Data communications | MW | S^3 | Done | Done |  | PkO has confirmed this
40 | ipappsrv | Personal Comms | MW | S^4 |  |  | Paulius Meskauskas | Pko is unaware until now, has been referred to the proposal. Wk50: Pinged pkO for a response. Wk 6: Pinged Paulius again for any updates
41 | ipconnmgmt | Data communications | MW | S^4 | Done | No access to hardware, timeframes unknown | Ville Leva / Tero Kaukola | Wk18: Wont happen in H1
42 | legacypresence | Productivity | MW | S^4 |  |  | Jukka Hamalainen | PkO has ruled out S^3, tentative on S^4. Confirmation awaited. Wk51: This is a S^4 target and pko is now making plans on validation. Time frames unknown.
43 | locationsrv | Location | MW | S^3 | Done | Done | Billy Gibson | Pko expects this to get over by wk52. Wk50: Asked for an update. Response pending. Wk 7: pinged pko confirms this is done
44 | mds | Multimedia | MW | S^3 | Done | No access to hardware | Henri Autio | Wk18: No visibility on SMP
45 | messagingmw | Productivity | MW | S^4 | Still work in progress |  | Harsha Sathyanarayana | PkO identified and contacted, 5th Nov - reminder sent. Wk50: Pinged pko again.
46 | metadatasrv | Multimedia | MW | S^3 | Done |  | Henri Autio | Wk18: No visibility on SMP
47 | mmappfw | Multimedia | MW | S^4 | Still work in progress |  | Jyrki Hoisko | Pko has no specific time frame info wk51: Contacted pkO for updates.
48 | mmmw | Multimedia | MW | S^4 |  |  | Aaron Roberts | Pko has been contacted again... No update yet. Wk 50: contacted pko again.
49 | mmuifw | Multimedia | MW | S^4 |  |  | Kumar Sohony | Pko unaware of SMP plans, have referred to proposal doc. Response awaited. Reminders sent once again. Wk51: No response from PkO. Have asked for updates once again.
50 | netprotocols | Data communications | MW | S^3 | Done | Done |  | PkO has confirmed this
51 | networkingdm | Device management | MW | S^3 | Done | n/a | Shobhit Singh | PkO has confirmed this. Wk 50: hw based validation pending. In touch with Pko. Merged with the remote mgmt package
52 | serviceapi | Runtimes | MW |  |  |  | Sunil Slathia
53 | serviceapifw | Runtimes | MW |  |  |  | Kasthurirengan
54 | opensrv | Productivity | MW | S^4 | n/a | n/a | Shrikumar B Sharma | Pk will be deprecated
55 | phonesrv | Personal Comms | MW | S^4 |  |  | Samu Collan | PkO sent reminder once again, wk 48: Package owner on holidays. Wk 50: Package owner seeks support from community.(?) for this activity. Wk51: Have referred to MH/Nokia. Wk 7: Pinged Paulius and still no change in updates.
56 | remoteconn | Device connectivity | MW | S^4 | Done | Done |  | Week 48, wk 50: PkO has confirmed SMP Safe. Hardware validation happening. Pko confirms hw validation done
57 | remotemgmt | Device management | MW | S^3 | Done | Done | deepak segaran | PkO aims to complete this by H2/2009. Also includes networkingdm package
58 | remotestorage | Device connectivity | MW | S^4 | n/a | n/a |  | Week 48, wk 50: PkO reckons package might be dropped from TB10.1
59 | Securitysrv | Security | MW | S^3 | Done | Done | Timo Heikkinen | PkO has confirmed this wk50: hw validation pending, wk 7: pko update pending, Done -Done
60 | Service Discovery and usage | Device connectivity | MW | S^4 | Done | Done |  | Pko expects this to happen by week 48 and on TB 10.1, Wk 50: PkO confirms as completed
61 | platformtools | Tools | MW |  | n/a | n/a |  | Awaiting confirmation from PkO that SMP Safe may not apply for this package/tool
62 | shortlinkconn | Device connectivity | MW | S^3 |  |  | Tero Soukko | Week 52 is the target, target revised. End of February, wk 7: pinged dale self
63 | svgt | UI | MW | S^4 |  |  | Mahesh Chaudri | Wk 16: PkO unwilling to commit deadline.
64 | uiaccelerator | UI | MW | S^4 |  |  | Markus Penttilla | Wk16: PkO unwilling to comment on SMP Plans, but reckons Pk is generally SMP Safe
65 | uiresources | UI | MW |  | n/a | n/a | Zhang Yong | PkO is unaware until now. Hasnt responded to reminders. Nov 17th : Steven Yao-PkO has asked for H/W to validate. Have referred to MH/Nokia. Wk51: No updates yet. Contacted again. Pk will be deprecated since part of avkon
66 | uitools | Tools | MW | S^3 | n/a | n/a | William Xu | PkO confirms all this to be Linux / Windows tools and hence not necessary to be SMP Safe.
67 | usbservices | Device connectivity | MW | S^3 | Done | Delayed until wk 44 | Xialong Shi | Delayed until wk 44
68 | videoutils | Multimedia | MW | S^4 | n/a | n/a | Petri Laine | Pko unaware of SMP plans, have referred to proposal doc. Wk 48: Had told pkO about ensuring SMPSafe for S^4 release, as this one's a MW pk. Wk 8: Pk owner reckons that this package may not be used/necessary in S^4. and hence doesnt plan for validation
69 | vpnclient | Data communications | MW | S^3 |  |  | Mikko Aittola | Wk 16: PkO unwilling to commit deadline.
70 | websrv | Runtimes | MW | S^3 | Done | Done | Sandeep Sahoo | PkO confirms this and SMP Safe code to be made available as early as week 45
71 | wirelessacc | Data communications | MW | S^3 | 2H/2009 | No access to hardware, timeframes unknown | Ville Leva | PkO yet to confirm.. Response awaited. Wk 4, wk 7: pko update pending, Pko does not intend to complete validation activity for the next few months
72 | searchsrv | Productivity | MW |  |  |  | Shreekanth Lakshmeshwar | New package.
73 | web | Runtimes | MW |  |  |  | Leonid Ebril
74 | devicectrl | Device management | APP | S^3 | Done | Done | deepak segaran | Pko expects this to happen by Q4/2009
75 | commonemail | Productivity | APP | S^4 |  |  | Mikko Bertin | Pko contacted. Response awaited, wk 50: PkO has been pinged again
76 | camera | Multimedia applications | APP | S^4 |  |  | Teemu Rossi | Pko contacted. Response awaited, wk: 50: PkO will get back next week.
77 | Connectivity Tools | Data communications | APP | S^4 | Done | H2 2010 | Tommi Rantanen | Wk 16: No access to hardware and hence not before H2 2010
78 | contacts | Productivity | APP | S^4 | wk18 | wk18 | Markku Kaurila | PKO confirms this is wk18/2010 target
79 | contentcontrol | Device management | APP | S^4 |  |  | Chetana savalgi | PkO will provide details on schedule eventually
80 | conversations | Productivity | APP | S^4 | n/a | n/a | Shrikumar B Sharma | conversations package will be deprecated from S^4
81 | dictionary | Productivity | APP |  | n/a | n/a | Wang xiaoyun | Package may be deprecated from TB 10.1
82 | files | Productivity | APP | S^4 | work in progress |  | Wang xiaoyun | Wk 16: Week 26 is the target now.
83 | media gallery | Multimedia applications | APP |  | n/a | n/a | Senthil Ganesan | No update from PkO, wk 50: pinged pko again for a response. , pk will be deprecated
84 | graphicsuis | UI | APP | S^4 |  |  | Chinmaya Padhi / Kumar Sohony | Pko contacted. Response awaited, wk48: pKO promised to get back by wk 49. Wk 50: Pinged PkO for a response again. Wk51: No response yet. Pinged once again.
85 | helps | UI | APP |  | n/a | n/a | Zhang Peng Cheng | Pko contacted. Wk 50: PkO needs help and hence has been redirected to contact MH/Nokia for hw support - package will be deprecated from S^4
86 | homescreen | UI | APP | S^4 | work in progress |  | Jaakko Haukipuro | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
87 | homescreentools | UI | APP | S^4 | work in progress |  | Jaakko Haukipuro | Pko contacted. Response awaited, wk 48: PkO is looking for hw to validate SMP Safe. But generally reckons package should be SMP Safe otherwise.
88 | im | Productivity | APP |  | n/a | n/a | Shrikumar B Sharma | This package will be merged into imsrv from S^4
89 | imgeditor | Multimedia applications | APP | S^4 |  |  | Mikael Laine | Pko contacted. Response awaited, wk 50: pinged again for a response , contacted ixonos
90 | imgvieweruis | Multimedia applications | APP |  | n/a | n/a | Senthil Ganesan | Pko contacted. Response awaited, wk 50: pinged again for a response, pk will be deprecated from S^4
91 | iptelephony | Personal Comms | APP | S^4 |  |  | Marko Sironen | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
92 | Mobile runtime for Java apps | Runtimes | APP | S^5 | ??? | ??? | Jyrki Aarnos | Wk 16: Pk confirms S^5 target. Discussing with them about Nokia SMP proposal deadlines.
93 | speechsrv | UI | APP | S^4 | n/a | n/a | Esa Seppala | PkO will provide details on schedule eventually, wk7: pk will be dropped from S^4, availability on future Symbian platforms to be decided eventually
94 | settingsuis | Device Management | APP | S^4 | Q2 | Q2 | Wang xiaoyun | targeted for Q2/2010
95 | utils | Productivity | APP | S^4 | n/a | n/a | Wang xiaoyun | wk 16 update: No plan to release this in S^4. Plans beyond that are unknown presently.
96 | musicplayer | Multimedia applications | APP | S^4 | work in progress |  | Jyrki Hoisko | H1/2010
97 | Voice Recorder | Multimedia applications | APP | S^4 | work in progress |  | Jyrki Hoisko | H1/2010, wk 8: pinged package owner for an update on this.
98 | printing | Device connectivity | APP | S^4 | n/a | n/a | Feng Li | Package is dropped from TB 10.1
99 | messaging | Productivity | APP | S^4 | work in progress |  | Shrikumar B Sharma | Q1/2010
100 | organizer | Productivity | APP | S^4 | work in progress |  | Sharad Upadhyay | Wk16: PkO has no SMP plans. Further discussions in progress
101 | location | Location | APP | S^3 | Done | Done | Billy Gibson | end of feb , wk 8: pinged pko. Pko confirms done-done
102 | mmsharinguis | Personal Comms | APP | S^4 |  |  | Paulius Meskauskas | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
103 | phone | Personal Comms | APP | S^4 |  |  | Samu Collan | Pko contacted. Response awaited, wk 50: PkO has no plans for SMP Safe validation. Wk 7: pinged paulius and no change in status
104 | photos | Multimedia applications | APP | S^4 |  |  | Senthil Ganesan | PkO yet to respond: Wk 50: sent out a reminder to PkO again.
105 | poc | Personal Comms | APP | S^4 | n/a | n/a | Wenqing wu | S^2 package, no plans to carry this pkg forward
106 | videotelephony | Personal Comms | APP | S^3 |  |  | Wenqing wu | PkO unaware of SMP plans. Wk 8: pinged pko for a response
107 | profile | UI | APP | S^4 |  |  | Dick Zhai | Wk 16: PkO has no SMP plans. Further discussions in progress.
108 | radio | Multimedia applications | APP | S^4 |  |  | Jyrki Hoisko | Wk16: PkO unable to commit deadlines. Will take up SMP activity shortly.
109 | screensaver | UI | APP |  | n/a | n/a | Robin Shi | Hardware availability issues - written to Mark Hambleton/Nokia - package will be deprecated from S^4
110 | techview | UI | APP | S^4 |  |  | Richard Potter | PkO yet to respond: Wk 50: sent out a reminder to PkO again., New package owner : no response yet, wk 8: pinged package owner
111 | videocenter | Multimedia applications | APP |  | n/a | n/a | Petri Laine | Pkg will be deprecated from S^4
112 | videoeditor | Multimedia applications | APP | S^4 |  |  | Mikael Laine | PkO yet to respond: Wk 50: sent out a reminder to PkO again. Wk 5/7: Contacted ixonos
113 | videoplayer | Multimedia applications | APP | S^4 |  |  | Petri Laine | PkO yet to respond: Wk 50: sent out a reminder to PkO again. Wk 2, wk 6, wk 8: pinged package owner for updates
114 | podcatcher | Multimedia applications | APP |  |  |  | Lars Persson | New package
115 | search | Productivity | APP |  |  |  | Shreekanth Lakshmeshwar | New package
116 | webuis | Runtimes | APP |  |  |  | Leonid Ebril
117 | Connectivity Tools | Data communications | App |  |  |  | Tommi Rantanen
118 | Desktop connectivity & PC Suite | Device connectivity | Desktop |  | n/a | n/a | Jyrki Hokkanen
119 | Printing | Device connectivity |  |  |  |  | Feng Li
120 | Service Discovery and usage | Device connectivity |  |  |  |  | Guruprasad Kini
121 | Gstreamer | Multimedia | MW |  |  |  | Harsh Jahagirdar
122 | openmaxil | Multimedia | OS |  |  |  | Juan Rubio
123 | internetradio | Multimedia applications | APP |  |  |  | Gang Shen
124 | Social Mobile framework | Productivity | MW |  |  |  | Chandradeep Gandhi
125 | Flashlite | Runtimes |  |  |  |  | Hema Chilukuri
126 | Qt | Runtimes |  |  |  |  | Eero Pentinen
127 | Webextensions | Runtimes |  |  |  |  | Salvatore Rinaldo
128 | Devicedebug | Tools |  |  |  |  | Ravi Kurupati
129 | Dynamic Analysis | Tools |  |  |  |  | Matti Laitinen
130 | Eclipse IDE | Tools |  |  |  |  | Ken Ryall

## Tools Plan
Package | Bug ID | Key Feature | Description | Misc | 2010 - Approx delivery schedule | [12 empty] | 2011
[5 empty] | wk 29 | wk 31 | wk 33 | wk 35 | wk 37 | wk 39 | wk 41 | wk 43 | wk 45 | wk 47 | wk 49 | wk 51 | wk 53
Build |  |  |  | Backlog published. Current features are not considered Key Features
Device Debug services | 1441 | Support for new run mode debug API | bar: 2010 - Approx delivery schedule wk 43
| 1444 | Support for Eclipse target communication framework protocol in TRK agent | bar: 2010 - Approx delivery schedule wk 43
Dynamic Analysis |  |  |  | Backlog info awaited
Eclipse IDE |  |  |  | No response from PkO
SDK Creation |  |  |  | Backlog info awaited
Static analysis |  |  |  | Backlog info awaited
Stubs |  |  |  | Backlog info awaited
SW System Configuration |  |  |  | No response from PkO
Test package |  |  |  | Backlog published. Current features are not considered Key Features
UI |  |  |  | No response from PkO
UI Tools | 3629 | Porting UI tools to Linux
WRT Tools |  |  |  | Backlog published. Current features are not considered Key Features

## pending bklog (hidden)
Key? |  | tag
| Wireless_Access/Backlog | Freeway | New Symbian Comms Architecture - A migration to Freeway architecture. |  | 2H/2009 | In development
| Ipappsrv_backlog | NGA | Support for NGA | 2H/2009 | 2H/2009 | In Development.
| Video_Player_Package/Backlog | NGA | Symbian NGA support for video playback Link to feature description | 2009-08-01 | &lt;MCL date&gt; | In development
| VideoTelephony_roadmap | NGA | NGA implemetaion of Video render | 2H/2009 | 2H/2009 | In Development
| Commsfw_Backlog | SMP | SMP | SMP enhanced comms framework | 2010 |  | Proposed
| Graphics_Package/Backlog | SMP | SMP safe - support for multi-core processors |  | 1H/09 (S^3) | In Development
| IP_Connection_Management_Package/Backlog | SMP | Ipconnmgmt SMP-safe: Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Messaging_Package/Backlog | SMP | SMP analysis/ support for messaging |  |  | Proposed
| Vpnclient_Package/Backlog | SMP | SMP safe phase 1 | 2H09 | Planned
| WLAN_Package_Backlog | SMP | SMP safeSupport for multicore processors |  | 2H/09 (SF^3) | Planned
| Wireless_Access/Backlog | SMP | SMP safe verification - Software runs in multiprocessor system. |  | 2H/2009 | Planned
| Access_Security_Package/Backlog | newUI | Implementation of Access Security UIs with Qt | N/A | 2010 1Q | Planned
| Application_Installation_Package/Backlog | newUI | Qt-based AppInstall UI components | Q1 2010 | Q1 2010 | Proposed
| Connectivity_Tools_Package/Backlog | newUI | Qt/Orbit migration for ConnTest | 2H/2009 | 1H/2010 | Proposed
| DRM_Package/Backlog | newUI | Qt-based DRM UI components | Q1 2010 | Q1 2010 | Proposed
yes | IDE_Package/Backlog | newUI | Qt Eclipse integration plugins version 1.5.2 | n/a | Aug 09 | in-progress
| IP_Connection_Management_Package/Backlog | newUI | DirectUI implementation: Orbit implementation of ipconnmgmt UI components. | 2H/2009 | 1H/2010 | Planned
yes | Location_Package/Backlog | newUI | Location UI enhancements with Qt | TBD | TBD | Proposed
yes | Messaging_Package/Backlog | newUI | Conversation based messaging direct touch UI using Qt | 2010-05-01 |  | Ongoing
yes | Phone_backlog | newUI | Call sliders to touch UI (new UI for answering the call while the device screen is locked) | 2H/2009 | 2H/2009 | In Development
yes | Phone_backlog | newUI | Direct UI | 1H/2010 | 1H/2010 | In Development
| Profile_Package/Backlog | newUI | QT'fication of Profiles |  |  | Planned
| Security_Services_Package/Backlog | newUI | Qt-based Securitysrv UI components | Q1 2010 | Q1 2010 | Proposed
yes | VideoTelephony_roadmap | newUI | touch UI support (implementation of common UI API) | 1H/2010 | 1H/2010 | In Development
| Wireless_Access/Backlog | newUI | DirectUI implementation - Orbit (Qt) implementation of wirelessacc UI components. |  | 1H/2010 | Proposed
| Wireless_Access/Backlog | newUI | DirectUI implementation - Replace WLAN Sniffer with Connect Screen. | 2H/2009 | 1H/2010 | Planned

## pdk3.0.d (hidden)
BUG ID | Title | KF | Contrib | Package
575 | Support for files over 2GB | 2GB files | NOKIA | imghandling
587 | Support for over 2GB files | 2GB files | NOKIA | mds
661 | Local Location Based Triggering Enhancements | LBS | NOKIA | Locationserv
245 | Symbian NGA support for video playback Link to feature description | NGA | NOKIA | Video player
268 | Homescreen page management | Multipage HS | NOKIA | HomeScreen
Note on B3: victorp: recieved information that this has been done, checking with package owner when